## All Local SEO Tools
📍 LOCAL SEO TOOLS — Complete Master List ¦ All Free APIs ¦ Zero Budget
Covering: GBP Tools • NAP & Citations • Schema • Keywords • Reviews • Content • Link Building • AI/GEO SEO
# | Tool Name | Free API / Method | What It Does | Difficulty | Priority
🏪 GBP & Google Tools
1 | Google Review Link Generator | Pure JS — construct Place ID URL | Generates a direct link customers click to leave a Google review | 🟢 Easy | 🔴 HIGH
2 | Google Review QR Code Generator | qrcode.js (open source JS lib) | Creates QR code from review link — print on receipts/flyers | 🟢 Easy | 🔴 HIGH
3 | Google Place ID Finder | Google Maps embed iframe | Finds the unique Place ID for any business on Google | 🟢 Easy | 🟡 MED
4 | GBP Optimization Score Checker | Checklist UI — self-audit form | Scores GBP completeness across 20+ factors (photos, hours, posts, etc.) | 🟢 Easy | 🔴 HIGH
5 | GBP Post Idea Generator | Template-based / Claude API free tier | Generates weekly GBP post ideas by business category | 🟢 Easy | 🟡 MED
6 | Google Maps Embed Generator | Google Maps Embed API (free key) | Generates iframe embed code for any address — drop on any webpage | 🟢 Easy | 🔴 HIGH
7 | Google Directions Link Generator | Pure JS — maps.google.com URL builder | Creates a one-click directions link to any business address | 🟢 Easy | 🟡 MED
8 | Google Business Category Finder | Static JSON — all ~4,000 GBP categories | Searchable list of every official GBP category to pick the right one | 🟢 Easy | 🟡 MED
9 | GBP Post Generator | Template-based (What's New/Offer/Event) | Generates ready-to-publish GBP posts with CTA and character limit | 🟢 Easy | 🟢 LOW
10 | GBP Profile Completeness Checklist | Interactive checklist UI | 50-point checklist covering every GBP field for maximum visibility | 🟢 Easy | 🟡 MED
📍 NAP & Citation Tools
11 | NAP Consistency Checker | HTTP fetch + HTML parse directories | Checks Name, Address, Phone consistency across Google, Yelp, YP, BBB, Manta | 🟡 Medium | 🔴 HIGH
12 | NAP Formatter / Normalizer | Pure JS | Standardizes phone formats and address abbreviations (St→Street, etc.) | 🟢 Easy | 🟡 MED
13 | Local Citation Finder | Overpass API (OpenStreetMap — free) | Finds where a business is already listed across the web | 🟡 Medium | 🟡 MED
14 | Citation Site List by Industry | Static curated database | Shows top citation directories sorted by niche (plumber, dentist, lawyer etc.) | 🟢 Easy | 🟡 MED
15 | Directory Submission Links Tool | Static curated list | One-click links to submit business to Yelp, YP, BBB, Manta, Foursquare etc. | 🟢 Easy | 🟢 LOW
16 | Duplicate Listing Detector | HTTP fetch multiple directories | Detects if the same business appears multiple times on one platform | 🟡 Medium | 🟡 MED
📐 Local Schema & Structured Data
17 | Local Business Schema Generator | Pure form → JSON-LD output | Full LocalBusiness schema with name, address, phone, hours, geo coordinates | 🟢 Easy | 🔴 HIGH
18 | Opening Hours Schema Generator | Pure form → openingHoursSpecification | Generates day-by-day opening hours in Google's preferred JSON-LD format | 🟢 Easy | 🔴 HIGH
19 | Service Area Schema Generator | Pure form → areaServed array | Builds schema markup listing all cities/regions a service business covers | 🟢 Easy | 🟡 MED
20 | Review / Rating Schema Generator | Pure form → AggregateRating JSON-LD | Generates star rating markup that displays in Google search results | 🟢 Easy | 🔴 HIGH
21 | FAQ Schema Generator (Local) | Pure form → FAQ JSON-LD | Creates FAQ schema for common local questions (hours, parking, pricing) | 🟢 Easy | 🟡 MED
22 | Local Business Schema Validator | Fetch page + parse + validate JSON-LD | Checks existing schema for missing required fields and errors | 🟡 Medium | 🔴 HIGH
23 | Geo Coordinates Finder | Nominatim API (OSM — free, no key) | Converts any address to lat/long coordinates for use in schema markup | 🟢 Easy | 🟡 MED
24 | Breadcrumb Schema Generator | Pure form → JSON-LD | Generates breadcrumb structured data for local pages | 🟢 Easy | 🟢 LOW
🔑 Local Keyword & Content Tools
25 | 'Near Me' Keyword Generator | Pure logic — service + location combos | Generates 'plumber near me', 'best dentist in [city]' keyword variations | 🟢 Easy | 🔴 HIGH
26 | Local Keyword Generator | Google Autocomplete (unofficial, free) | Suggests local keywords by combining service type + city | 🟡 Medium | 🔴 HIGH
27 | City × Service Keyword Combinator | Pure JS — bulk keyword matrix | Bulk-combines service keywords × city list to find targeting opportunities | 🟢 Easy | 🟡 MED
28 | Long-tail Local Keyword Builder | Pure logic — pattern builder | Creates long-tail patterns: 'best [service] in [city] [year]' | 🟢 Easy | 🟡 MED
29 | Location Page Generator | Pure form + SEO template | Generates complete SEO-optimised location landing page copy | 🟢 Easy | 🔴 HIGH
30 | Local Meta Title & Desc Generator | Pure form — city+service patterns | Creates optimised meta title + description for local service pages | 🟢 Easy | 🔴 HIGH
31 | Service Area Page Content Generator | Template + pure logic | Generates service-area-specific page copy for multi-location businesses | 🟢 Easy | 🟡 MED
32 | Local FAQ Generator | Pure form — by business type | Auto-generates common local FAQs based on business category | 🟢 Easy | 🟡 MED
33 | Local Business Description Generator | Templates / Claude API free tier | Generates GBP business descriptions within 750 character limit | 🟡 Medium | 🟡 MED
⭐ Review & Reputation Tools
34 | Review Response Generator | Claude API free tier / templates | Generates professional, personalised responses to Google reviews | 🟡 Medium | 🔴 HIGH
35 | Review Request Email/SMS Templates | Pure form + template library | Creates customisable review request messages for after-service follow-up | 🟢 Easy | 🔴 HIGH
36 | Negative Review Response Templates | Static categorised templates | Ready-to-use professional replies for common negative review scenarios | 🟢 Easy | 🟡 MED
37 | Yelp / Trustpilot Review Link Gen | Pure logic — build platform review URLs | Creates direct review links for Yelp, Trustpilot, Facebook and more | 🟢 Easy | 🟡 MED
38 | Review Platform Finder | BizData API (free, no key) | Shows all platforms where a business is already listed and reviewable | 🟡 Medium | 🟢 LOW
39 | Star Rating Schema Generator | Pure form → AggregateRating markup | Adds star rating structured data so reviews appear in Google SERPs | 🟢 Easy | 🟡 MED
🗺️ Local Business Data & Map Tools
40 | Local Business Finder | BizData API (free, no key) + Overpass | Search local businesses by type + location using open data | 🟡 Medium | 🟡 MED
41 | Competitor Local SEO Analyzer | HTTP fetch + HTML parse | Analyzes competitor's local page for schema, NAP, meta tags and GBP signals | 🟡 Medium | 🔴 HIGH
42 | Local Pack Eligibility Checker | Checklist UI — 40 ranking factors | Self-audit tool checking all factors Google uses for Map Pack ranking | 🟢 Easy | 🔴 HIGH
43 | Service Radius Calculator | Pure JS + Leaflet.js (free open source) | Draws a service-area radius on an interactive map from a business address | 🟡 Medium | 🔴 HIGH
44 | Local Competitor Map | Overpass API + Leaflet.js | Shows all nearby competitors pinned on an interactive map | 🟡 Medium | 🟡 MED
45 | Address Geocoder | Nominatim OSM (free, 1 req/sec) | Converts any street address to GPS lat/long coordinates | 🟢 Easy | 🟢 LOW
46 | Business Hours Formatter | Pure JS | Converts business hours to JSON-LD, iCal, and plain text formats | 🟢 Easy | 🟢 LOW
🖼️ Image & Media Tools
47 | Image Geo-Tagging Tool | Pure JS — EXIF write library (exifr) | Adds GPS coordinates (EXIF data) to images for local SEO signals | 🟡 Medium | 🔴 HIGH
48 | Image Alt Text Generator | Claude API free tier | Generates SEO-optimised alt text for business images | 🟡 Medium | 🟡 MED
49 | Image Compressor (Local SEO) | Canvas API — client-side JS | Compresses images for faster page load — key local ranking factor | 🟡 Medium | 🟡 MED
50 | Google Maps Screenshot Downloader | Pure JS — Google Maps Static embed | Downloads static Google Maps image for use on location pages | 🟡 Medium | 🟢 LOW
🔗 Local Link & Citation Building
51 | Niche Directory Finder | Overpass + static DB by business type | Finds industry-specific directories (plumbing, medical, legal etc.) | 🟡 Medium | 🟡 MED
52 | Local Link Prospector | HTTP fetch + HTML parse | Finds local sponsorship, chamber, event pages for link building | 🟡 Medium | 🟡 MED
53 | Unlinked Brand Mention Finder | Google Search query builder | Surfaces brand mentions across the web that don't link back to the site | 🟢 Easy | 🟡 MED
54 | Local Citation Site List | Static database — 50+ directories | Sorted list of top local citation sites by country and niche | 🟢 Easy | 🟡 MED
🤖 AI / GEO SEO Tools (2025-26 Trend)
55 | AI Model Index Checker | Fetch robots.txt + parse AI bot rules | Checks if GPTBot, ClaudeBot, Gemini, Perplexity can crawl the site | 🟢 Easy | 🔴 HIGH
56 | LLMs.txt Generator | Sitemap crawl → generate llms.txt | Creates llms.txt file to guide AI models in understanding site content | 🟡 Medium | 🔴 HIGH
57 | Local E-E-A-T Score Checker | HTML analysis — author, schema, about | Checks E-E-A-T signals Google uses to rank local business pages | 🟡 Medium | 🔴 HIGH
58 | AI Overview Readiness Checker | HTML + schema + structured data check | Tests if page is optimised to appear in Google's AI Overviews | 🟡 Medium | 🔴 HIGH
59 | SERP Snippet Simulator | Pure JS — pixel-width simulation | Previews exactly how a page title + description appears in Google search | 🟢 Easy | 🔴 HIGH
60 | Bulk DR Checker | Ahrefs Free API — no key needed | Checks Domain Rating for multiple URLs at once — no API key required | 🟢 Easy | 🔴 HIGH
📊 SUMMARY: 60 Local SEO Tools ¦ 🔴 HIGH Priority: 26 tools ¦ 🟡 MED: 26 tools ¦ 🟢 LOW: 8 tools ¦ All APIs: $0 Cost

## Launch Plan — 10 Tools
🚀 LOCAL SEO TOOLS — LAUNCH PLAN ¦ 10 Priority Tools ¦ 1 Tool Every 2 Weeks
Strategy: Content writer produces 1 tool's content every 2 weeks → Dev builds tool → QA + Launch → Total timeline: 20 Weeks (5 Months)
🔴 = Dev builds tool ¦ ✍️ = Content writer task ¦ 🟢 = Launch ready ¦ ⭐ = High traffic potential ¦ 💰 = Revenue driver
# | Tool Name | Sprint (Weeks) | Launch Target | Free API / Tech Stack | Content Writer Tasks | Dev Tasks | Traffic Potential | Status
TOOL 1 — Google Review Link Generator ¦ Week 1–2 ¦ Launch: Week 2
1 | Google Review Link Generator | Week 1–2 | Week 2 | Pure JS Google Place ID URL | ✍️ Write guide: 'How to Get More Google Reviews' ✍️ Tool description (300 words) ✍️ FAQ section (5 Qs) ✍️ Meta title + description | 🔴 Build Place ID search input 🔴 Auto-construct review URL 🔴 QR code generation 🔴 Copy-to-clipboard button | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
TOOL 2 — GBP Optimization Score Checker ¦ Week 3–4 ¦ Launch: Week 4
2 | GBP Optimization Score Checker | Week 3–4 | Week 4 | Checklist logic — Pure JS No API needed | ✍️ Write '20 Ways to Optimize Google Business Profile' ✍️ Scoring criteria explanation ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Build 20-point scoring form 🔴 Score calculator logic 🔴 Recommendations engine 🔴 Printable report output | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
TOOL 3 — Local Business Schema Generator ¦ Week 5–6 ¦ Launch: Week 6
3 | Local Business Schema Generator | Week 5–6 | Week 6 | Pure form → JSON-LD output No API needed | ✍️ Write 'Local Business Schema: Complete Guide' ✍️ Explain each field (name, address, hours, geo) ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Build multi-field form 🔴 JSON-LD generator logic 🔴 Live preview panel 🔴 Copy/download output 🔴 Validation checker | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
TOOL 4 — SERP Snippet Simulator ¦ Week 7–8 ¦ Launch: Week 8
4 | SERP Snippet Simulator | Week 7–8 | Week 8 | Pure JS Pixel-width simulation | ✍️ Write 'How to Write Perfect Title Tags & Meta Descriptions' ✍️ Character limit guide ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Build title/desc input fields 🔴 Google SERP visual preview 🔴 Pixel-width counter (600px title, 920px desc) 🔴 Mobile vs Desktop toggle 🔴 Character warning colours | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
TOOL 5 — Bulk DR Checker ¦ Week 9–10 ¦ Launch: Week 10
5 | Bulk DR Checker | Week 9–10 | Week 10 | Ahrefs Free API (No API key needed!) ahrefs.com/v3/public/domain-rating-free | ✍️ Write 'What is Domain Rating & Why It Matters for Local SEO' ✍️ How to interpret DR scores ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Bulk URL textarea input 🔴 Loop Ahrefs free API calls 🔴 Results table with DR scores 🔴 Export to CSV button 🔴 Rate limit handling | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
TOOL 6 — Image Geo-Tagging Tool ¦ Week 11–12 ¦ Launch: Week 12
6 | Image Geo-Tagging Tool | Week 11–12 | Week 12 | exifr.js (open source) Pure client-side JS No upload to server | ✍️ Write 'Image Geo-Tagging for Local SEO: Full Guide' ✍️ Why EXIF GPS data matters for local ranking ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Image upload (client-side) 🔴 Address → GPS via Nominatim 🔴 Write EXIF GPS coords with exifr.js 🔴 Download tagged image 🔴 Bulk image support | ⭐⭐⭐⭐ High | 📋 PLAN
TOOL 7 — NAP Consistency Checker ¦ Week 13–14 ¦ Launch: Week 14
7 | NAP Consistency Checker | Week 13–14 | Week 14 | HTTP fetch + HTML parse Check Yelp, YP, BBB, Manta No API needed | ✍️ Write 'NAP Consistency: The #1 Local SEO Factor' ✍️ List all major citation sources ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 NAP input form (name, address, phone) 🔴 Fetch & parse 10 major directories 🔴 Side-by-side comparison table 🔴 Mismatch highlighting 🔴 Fix recommendations | ⭐⭐⭐⭐ High | 📋 PLAN
TOOL 8 — Review Response Generator ¦ Week 15–16 ¦ Launch: Week 16
8 | Review Response Generator | Week 15–16 | Week 16 | Template library + Claude API (Free tier — no cost) LanguageTool for grammar | ✍️ Write 'How to Respond to Google Reviews (Good & Bad)' ✍️ 20 response templates by review type ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Review text input 🔴 Sentiment detection (positive/negative) 🔴 Category selector (food, service etc.) 🔴 Claude API integration (free) 🔴 Copy to clipboard | ⭐⭐⭐⭐ High | 📋 PLAN
TOOL 9 — 'Near Me' Keyword Generator ¦ Week 17–18 ¦ Launch: Week 18
9 | 'Near Me' Keyword Generator | Week 17–18 | Week 18 | Pure JS keyword logic Google Autocomplete (unofficial, free) No API key | ✍️ Write 'Near Me Keywords: How to Rank for Local Searches' ✍️ List 100 near me keyword patterns ✍️ Tool description + FAQ ✍️ Meta tags | 🔴 Business type input 🔴 City/location input 🔴 Generate keyword matrix (50+ variants) 🔴 Google Autocomplete integration 🔴 Export to CSV | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
TOOL 10 — Local SEO Audit Checklist ¦ Week 19–20 ¦ Launch: Week 20
10 | Local SEO Audit Checklist | Week 19–20 | Week 20 | Interactive checklist UI Pure JS — no API needed | ✍️ Write '50-Point Local SEO Audit: Complete Checklist' ✍️ Explain each audit point ✍️ Tool description + FAQ ✍️ Meta tags + Schema | 🔴 50-point interactive checklist 🔴 Category grouping (GBP, NAP, On-page, Links) 🔴 Score calculator (pass/fail) 🔴 PDF export of results 🔴 Share results link | ⭐⭐⭐⭐⭐ Very High | 📋 PLAN
📅 TIMELINE SUMMARY — 20 WEEKS TOTAL
Weeks 1–2 | Tool 1: Google Review Link Generator |  | Content: Review guide + FAQ + meta |  |  | Dev: JS URL builder + QR code
Weeks 3–4 | Tool 2: GBP Optimization Score |  | Content: GBP optimization guide + FAQ |  |  | Dev: Scoring form + recommendations
Weeks 5–6 | Tool 3: Local Business Schema Generator |  | Content: Schema complete guide + FAQ |  |  | Dev: Form + JSON-LD generator
Weeks 7–8 | Tool 4: SERP Snippet Simulator |  | Content: Title tag + meta desc guide |  |  | Dev: Pixel-width preview tool
Weeks 9–10 | Tool 5: Bulk DR Checker |  | Content: Domain Rating guide for local SEO |  |  | Dev: Ahrefs free API integration
Weeks 11–12 | Tool 6: Image Geo-Tagging Tool |  | Content: EXIF geo-tagging local SEO guide |  |  | Dev: exifr.js + Nominatim
Weeks 13–14 | Tool 7: NAP Consistency Checker |  | Content: NAP consistency complete guide |  |  | Dev: HTTP fetch + parse directories
Weeks 15–16 | Tool 8: Review Response Generator |  | Content: How to respond to reviews guide |  |  | Dev: Claude API + template system
Weeks 17–18 | Tool 9: Near Me Keyword Generator |  | Content: Near me keywords ranking guide |  |  | Dev: Keyword matrix + autocomplete
Weeks 19–20 | Tool 10: Local SEO Audit Checklist |  | Content: 50-point local SEO audit guide |  |  | Dev: Interactive checklist + PDF export
💡 NOTE: Each 2-week sprint = Week 1 (Content Writer finishes article + FAQ) → Week 2 (Dev builds tool, QA tests, tool goes live with content on same page) ¦ Target: 10 live local SEO tools by Week 20